## in
Actions_Taken | Affected_Orgs | Category | Date_Detected | Description | Detector | Downtime_Minutes | End_Date_Time | Incident_Status | Incident_Type | Lessons_Learned | Location | Phone | Ref | Root_Cause | Sart_Date_Time | Source | Systems_Affected
An email was sent to the ISP.¦¦An incident form was completed | All | System Downtime | 2026-03-20T19:13:00.000Z | Mainone Host downtime | Takyi Owusu Mensah | 420 | 2026-03-21T02:05:00.000Z | Resolved | Others | Proactive monitoring of internet traffics. Having a back up ISP | 3rd floor Heritage tower | 542672470 | INC_26_030166 | The link was impacted by a suspected fiber cut on our support partner network. | 2026-03-20T19:05:00.000Z | External | None as traffic was channelled through other ISP.
Traffic was switched temporary to the other ISP until mainone was stable.¦¦An incident report was completed. | All | System Downtime | 2026-03-19T16:05:00.000Z | Mainone host downtime | Takyi Owusu Mensah | 240 | 2026-03-19T20:15:00.000Z | Resolved | Others | Proactive monitoring of Internet speed and traffic. | 3rd floor Heritage tower | 542672470 | INC_26_030165 | Service outage was due a configuration error on the switch. | 2026-03-19T16:15:00.000Z | External | None as traffic was channelled through another ISP.
An email was sent to mainone informing them of the downtime.¦¦An incident form was completed.¦¦A ticket was create on the mainone customer portal | All | System Downtime | 2026-03-19T09:15:00.000Z | Mainone host was not reachable. | Takyi Owusu Mensah | 330 | 2026-03-19T14:50:00.000Z | Resolved | Others | Always have a back up ISP. Proactive monitoring of internet speed and traffic. | 3rd floor Heritage tower | 542672470 | INC_26_030164 | This was due to a to power failure at mainone last mile segment. | 2026-03-19T09:20:00.000Z | External | None as traffic was channelled through another ISP.
error was shared with the adsl team via mail¦¦The issue was resolved by the Adsl team | Telecel | System Downtime | 2026-03-17T06:55:00.000Z | Adsl transaction were failing because we were getting bad request response from them | Harry Opata | 7806 | 2026-03-22T17:01:00.000Z | Resolved | Service / Application not responding | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_030167 | we were getting bad request response from them | 2026-03-17T06:55:00.000Z | External | All transactions
Mails were sent to clients¦¦Issue was resolved by the AT team | AirtelTigo | System Downtime | 2026-03-15T00:00:00.000Z | Transactions were failing intermittently | Harry Opata | 480 | 2026-03-15T08:00:00.000Z | Resolved | System Maintenance | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_030163 | Transactions were failing intermittently because of a planned maintenance | 2026-03-15T00:00:00.000Z | External | All Transactions
Mails were sent to clients¦¦issue was resolved by mtn | MTN | System Downtime | 2026-03-14T22:00:00.000Z | MTN Transactions were failing intermittently | Harry Opata | 720 | 2026-03-15T10:00:00.000Z | Resolved | System Maintenance | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_030162 | Transactions were failing because of a planned maintenance | 2026-03-14T22:00:00.000Z | External | All transactions
Issue was resolved by Team MTN | MTN | System Downtime | 2026-03-14T20:00:00.000Z | Transactions were failing intermittenly | Harry Opata | 60 | 2026-03-14T21:00:00.000Z | Resolved | Service / Application not responding | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_030161 | Transactions experienced intermittent failures due to unplanned maintenance at that time. | 2026-03-14T20:00:00.000Z | External | Debit and Top up transactions
The issue was escalated to the Abii National Team and was resolved at their end | Abii National | System Downtime | 2026-03-14T09:37:00.000Z | We were not able to connect to their host | Mary Asante | 215 | 2026-03-14T13:11:00.000Z | Resolved | Connectivity Issue | We shoul monitor closely to detect such issues on time | 3rd floor Heritage tower | 534488985 | INC_26_030159 | Connectivity issue | 2026-03-14T09:36:00.000Z | External | All Abii National transactions
We escalated the issue to the Vision fund team | VisionFund | System Downtime | 2026-03-14T00:00:00.000Z | We couldn't connect to their host | Mary Asante | 849 | 2026-03-14T14:09:00.000Z | Resolved | Connectivity Issue | We should monitor closely to detect such issues on time | 3rd floor Heritage tower | 534488985 | INC_26_030160 | Connectivity issue | 2026-03-14T00:00:00.000Z | External | All Vision fund transactions
The issue was escalated to the DevOps team. And It was solved by them. | All | System Downtime | 2026-03-13T17:15:00.000Z | USSD Downtime | Anku Bright | 79 | 2026-03-12T18:38:00.000Z | Resolved | Server Failure / Shut Down | Continus monitoring | 3rd floor Heritage tower | 552756191 | INC_26_030158 | we experienced a technical issue affecting our 30.26 network segment, which impacted our USSD infrastructure and resulted in a temporary shutdown of all associated shortcodes. During this period, users may have experienced failed sessions or an inability to access services via USSD. | 2026-03-12T17:19:00.000Z | Internal | USSD Applications
Mails were sent to clients¦¦issue was resolved from our end | MTN | System Downtime | 2026-03-12T00:03:00.000Z | All Debit and Top up transactions were failing | Harry Opata | 95 | 2026-03-12T01:38:00.000Z | Resolved | Connectivity Issue | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_030157 | connectivity issue | 2026-03-12T00:03:00.000Z | Internal | All Debit and Top up transactions
Clients were informed about the maintenance schedule¦¦Clients were informed when the maintenance was over | MTN | System Downtime | 2026-03-10T01:00:00.000Z | System Maintenance | Eric Fillipe Arthur | 240 | 2026-03-10T05:00:00.000Z | Resolved | Connectivity Issue | Continuous monitoring and reporting | 3rd floor Heritage tower | 201471988 | INC_26_030156 | MTN Maintenance | 2026-03-10T01:00:00.000Z | External | Mobile Money / Vasgate
Issue was escalated to BESTPOINT team¦¦BESTPOINT team resolved the issue | Bestpoint | System Downtime | 2026-03-09T19:52:00.000Z | Server inaccessible | Eric Fillipe Arthur | 128 | 2026-03-09T22:00:00.000Z | Resolved | Connectivity Issue | Continuous monitoring and reporting | 3rd floor Heritage tower | 201471988 | INC_26_030155 | The team could not access BESTPOINT server | 2026-03-09T19:52:00.000Z | External | Mobile Money / Vasgate
The 30.17 server was restarted | All | System Downtime | 2026-03-08T06:43:00.000Z | We observed that the majority of debit transactions were in a pending state, and name verification could not be performed on Xcel. Upon investigation, we attempted to access server 30.17, but it was found to be unresponsive. With the assistance of Ezra Ohene and Takyi Owusu Mensah, we restarted the server, after which normal operations were restored and the issue was resolved | Anku Bright | 100 | 2026-03-08T08:20:00.000Z | Resolved | Service / Application not responding | Continuous monitoring | 3rd floor Heritage tower | 552756191 | INC_26_030153 | 30.17 was not accessible | 2026-03-08T06:40:00.000Z | Internal | Most debit transactions and Xcel name verification
Issue was escalated to PBL team¦¦PBL tech team resolved the issue from their end | PBL | System Downtime | 2026-03-06T07:20:00.000Z | Thier transactions were failing because we could not connect to their host | Maxwell Eshun | 603 | 2026-03-06T17:23:00.000Z | Resolved | Connectivity Issue | Continuous monitoring and asking for update till issue is resolved | 3rd floor Heritage tower | 533866740 | INC_26_030152 | Their CBA went off | 2026-03-06T07:20:00.000Z | External | Mobile Money and Vasgate
The Issue was escalated to the PBL team.¦¦The issue was resolved by the Pbl team | PBL | System Downtime | 2026-03-06T05:50:00.000Z | Transactions were failing we could not connect to their host | Harry Opata | 636 | 2026-03-06T16:26:00.000Z | Resolved | Connectivity Issue | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_030154 | We could not connect to their host. | 2026-03-06T05:50:00.000Z | External | All transactions
Issue was escalated to the PBL team¦¦The PBL team resolved the issue from their end | PBL | System Downtime | 2026-03-03T19:28:00.000Z | Connectivity Issue | Eric Fillipe Arthur | 262 | 2026-03-03T23:50:00.000Z | Resolved | Connectivity Issue | Continuous monitoring and reporting | 3rd floor Heritage tower | 201471988 | INC_26_030150 | We were not able to access the PBL server | 2026-03-03T19:28:00.000Z | External | Mobile Money / Vasgate
The issue was escalated to Devops | VisionFund | System Downtime | 2026-03-04T12:00:00.000Z | we were not able to reach Vision fund live endpoint | Simon Owusu Ansah | 256 | 2026-03-03T16:16:00.000Z | Resolved | Others | we should monior transactions after a configuration change | 3rd floor Heritage tower | 593489937 | INC_26_030151 | there was a configuration that was done that caused the endpoint to change from demo to live | 2026-03-03T12:00:00.000Z | Internal | momo
Issue was escalated to the network team | All | System Downtime | 2026-02-28T01:40:00.000Z | Internet connectivity | Eric Fillipe Arthur | 200 | 2026-02-28T05:00:00.000Z | Pending | Connectivity Issue | Continuous monitoring and reporting | 3rd floor Heritage tower | 201471988 | INC_26_020147 | No internet traffic | 2026-02-28T01:40:00.000Z | Internal | All systems / applications
A message was sent to Rancard via teams¦¦The issue was resolved from their end. | Telecel | System Downtime | 2026-02-27T23:00:00.000Z | Telecel airtime transactions were failing | Harry Opata | 480 | 2026-02-28T07:00:00.000Z | Pending | Service / Application not responding | There must be a continuous monitoring and asking of update from their team on the issue. | 3rd floor Heritage tower | 256591308 | INC_26_020148 | All telecel airtime transactions were failing because of connectivity issue | 2026-02-27T23:00:00.000Z | External | Vasgate
The issue was esclated to the DevOps team¦¦AKRB team was engaged and the issue was resolved at their end | Atwima | System Downtime | 2026-02-27T14:06:00.000Z | We were not able to establish connection with them. | Mary Asante | 68 | 2026-02-27T15:13:00.000Z | Resolved | Connectivity Issue | We should monitoer closely to detect such issues on time | 3rd floor Heritage tower | 533454143 | INC_26_020146 | Error response from their end | 2026-02-27T14:05:00.000Z | External | All AKRB transactions
Clients were informed about the maintenance activity¦¦Clients were informed when the maintenance activity was over | MTN | System Downtime | 2026-02-25T23:00:00.000Z | Scheduled Maintenance | Eric Fillipe Arthur | 360 | 2026-02-26T05:00:00.000Z | Resolved | System Maintenance | Continuous monitoring and reporting | 3rd floor Heritage tower | 201471988 | INC_26_020145 | Syatem Maintenance | 2026-02-25T23:00:00.000Z | External | Mobile Money / Vasgate
Isssue was escalated to the DEVOPS team¦¦DEVOPS team downloaded the latest certificate and replaced it with the old | Telecel | System Downtime | 2026-02-25T11:54:00.000Z | The SSL certificate expired causing VODA ADSL transactions to fail | Maxwell Eshun | 4642 | 2026-02-28T17:16:00.000Z | Resolved | Connectivity Issue | Continuous monitoring and askiung for update till issue is resolved | 3rd floor Heritage tower | 533866740 | INC_26_030149 | SSL CERTIFICATE EXPIRY | 2026-02-25T11:54:00.000Z | Internal | Telecel ADSL transactions
We checked the logs to know the root cause¦¦The issue was resolved at our end | MTN | System Downtime | 2026-02-24T20:48:00.000Z | irtime transactions were failing due to an expired SSL certificate. | Harry Opata | 102 | 2026-02-24T22:30:00.000Z | Resolved | Connectivity Issue | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_020144 | expired SSL certificate. | 2026-02-24T20:48:00.000Z | Internal | All Mtn airtime transactions
ISSUE WAS ESCALATED | AirtelTigo | System Downtime | 2026-02-24T00:00:00.000Z | DOWNTIME | Israel Opata | 0 | 2026-02-24T00:00:00.000Z | Resolved | Connectivity Issue | CONTINUOUS MONITORING | 3rd floor Heritage tower | 123456789 | INC_26_020143 | CONNECTION ISSUE | 2026-02-24T00:00:00.000Z | Internal | MOBILE MONEY
Issue was escalated to the finance team¦¦The finance team resolved the issue | ECG | System Downtime | 2026-02-18T18:59:00.000Z | Insufficient OVA | Eric Fillipe Arthur | 75 | 2026-02-18T20:14:00.000Z | Resolved | Others | Continuous monitoring and reporting | 3rd floor Heritage tower | 201471988 | INC_26_020142 | Insufficient OVA balance | 2026-02-18T18:59:00.000Z | Internal | ECG Transactions
All clients and Banks were inform via whatsApp and Mail | MTN | System Downtime | 2026-02-17T22:00:00.000Z | Planned Maintenance by MTN | Fredrick Hanson | 360 | 2026-02-18T04:00:00.000Z | Resolved | System Maintenance | Always just the schedule time time to confirm if maintenance has started and do same for the end time | 3rd floor Heritage tower | 552150123 | INC_26_020141 | Planned Maintenance | 2026-02-17T22:00:00.000Z | External | All MTN MoMo transactions
www | Telecel | System Downtime | 2026-02-17T11:00:00.000Z | Transactions were failing | Harry Opata | 90 | 2026-02-17T12:30:00.000Z | Pending | Connectivity Issue | www | 3rd floor Heritage tower | 256591308 | INC_26_020140 | Transactions were failing | 2026-02-17T11:00:00.000Z | External | All credit transactions
Reached out to the PBL team and waited for further updates | Bestpoint | System Downtime | 2026-02-17T10:54:00.000Z | Transactions were failing | Jacob Quarshie Nii Odoi | 61 | 2026-02-17T11:54:00.000Z | Resolved | Others | Improve on proactive monitoring | 3rd floor Heritage tower | 205688585 | INC_26_020139 | We couldnt access their server | 2026-02-17T10:53:00.000Z | External | ALL BESTPOINT TRANSACTIONS
Bestpoint Team notified and restored connection | Bestpoint | System Downtime | 2026-02-17T07:53:00.000Z | Bestpoint transactions were not going through. | Jacob Quarshie Nii Odoi | 22 | 2026-02-17T08:15:00.000Z | Resolved | Server Failure / Shut Down | There must be a continuous monitoring and asking of update from their team on the issue. | 3rd floor Heritage tower | 205688585 | INC_26_020138 | We were not able to access their server | 2026-02-17T07:53:00.000Z | External | All Bestpoint Transactions
Issue was escalated to BOA team to restart the server from their end¦¦BOA team restarted the server and resolved the issue | BOA | System Downtime | 2026-02-16T17:30:00.000Z | Connectivity error | Eric Fillipe Arthur | 824 | 2026-02-17T07:14:00.000Z | Resolved | Connectivity Issue | Continuous monitoring and reporting | 3rd floor Heritage tower | 201471988 | INC_26_020137 | The application could not connect to the database | 2026-02-16T17:30:00.000Z | Internal | Mobile Money / Vasgate
Issue was esclated to the pbl team via mail | PBL | System Downtime | 2026-02-16T02:46:00.000Z | Transactions were failing because we could not connect to their host | Harry Opata | 374 | 2026-02-16T09:00:00.000Z | Pending | Connectivity Issue | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_020136 | we could not connect to their host | 2026-02-16T02:46:00.000Z | External | All transactions
A call was made to a member of the pbl team¦¦A message containg the error was sent to their Teams page | PBL | System Downtime | 2026-02-16T01:58:00.000Z | Transactions were failing because we getting response 01 from their cba | Harry Opata | 45 | 2026-02-16T01:43:00.000Z | Resolved | Service / Application not responding | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_020133 | We were getting response code 01 from their cba | 2026-02-16T00:58:00.000Z | External | All Transactions
A mail was sent to all clients ¦¦Telecel restored service from their end | Telecel | System Downtime | 2026-02-15T22:10:00.000Z | All Telecel Transactions were failing | Harry Opata | 35 | 2026-02-15T22:45:00.000Z | Resolved | Connectivity Issue | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_020134 | All Telecel Transactions were failing | 2026-02-15T22:10:00.000Z | External | Credit Transactions
A message was sent to Rancard¦¦Rancard resolved the issue from their end | Telecel | System Downtime | 2026-02-15T19:37:00.000Z | Telecel airtime transactions were failing | Harry Opata | 32 | 2026-02-15T20:09:00.000Z | Resolved | Connectivity Issue | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_020135 | All telecel airtime transactions were failing because of connectivity issue | 2026-02-15T19:37:00.000Z | External | Vasgate
Connection was restored by MTN tech team | MTN | System Downtime | 2026-02-14T22:00:00.000Z | All MTN transactions were failing because of the maintenance | Maxwell Eshun | 720 | 2026-02-15T10:00:00.000Z | Resolved | System Maintenance | Continuous monitoring and asking for updates till issue is resolved | 3rd floor Heritage tower | 533866740 | INC_26_020132 | System maintenance | 2026-02-14T22:00:00.000Z | External | Mobile Money
Banks involved were notified¦¦The server was restarted to resolve the issue | PBL¦¦SISL | System Downtime | 2026-02-13T19:32:00.000Z | Server was down | Eric Fillipe Arthur | 160 | 2026-02-13T22:12:00.000Z | Resolved | Connectivity Issue | Continous monitoring and reporting | 3rd floor Heritage tower | 201471988 | INC_26_020131 | Both SISL and PBL transactions were not coming through because the server 172.16.30.27 was down | 2026-02-13T19:32:00.000Z | Internal | Mobile Money / Vasgate
A mail was sent to the NIB team | NIB | System Downtime | 2026-02-12T17:19:00.000Z | Transaction were not coming in because we could not connect to their server. | Harry Opata | 219 | 2026-02-12T20:58:00.000Z | Resolved | Connectivity Issue | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_020130 | we could not connect to their server. | 2026-02-12T17:19:00.000Z | External | All Transactions
Issue was escalated to PBL team¦¦PBL team resolved the issue | PBL | System Downtime | 2026-02-12T10:58:00.000Z | Error from PBL host | Eric Fillipe Arthur | 47 | 2026-02-12T11:45:00.000Z | Resolved | Connectivity Issue | Continuous monitoring and reporting | 3rd floor Heritage tower | 201471988 | INC_26_020129 | Difficulty connecting to PBL host | 2026-02-12T10:58:00.000Z | External | Mobile Money / Vasgate
PBL tech team was contacted via Teams & mail | PBL | System Downtime | 2026-02-11T13:07:00.000Z | PBL's server and host were down which was causing transactions to fail | Fredrick Hanson | 587 | 2026-02-11T22:56:00.000Z | Resolved | Service / Application not responding | There must be a continuous monitoring and asking of update from their team on the issue. | 3rd floor Heritage tower | 552150123 | INC_26_020128 | Their host was down | 2026-02-11T13:09:00.000Z | External | All PBL transactions
Issue was escalated to the NIB team¦¦The NIB team resolved the issue | NIB | System Downtime | 2026-02-09T15:19:00.000Z | Inability to connect to NIB sever | Eric Fillipe Arthur | 134 | 2026-02-09T17:33:00.000Z | Resolved | Connectivity Issue | Continuous monitoring and reporting | 3rd floor Heritage tower | 201471988 | INC_26_020127 | NIB server was not accessible | 2026-02-09T15:19:00.000Z | External | Mobile Money / Vasgate
We restarted the CBA and the CMS | Atwima | System Downtime | 2026-02-09T07:10:00.000Z | Transactions wre not coming in due to binding issue | Eric Fillipe Arthur | 320 | 2026-02-09T12:30:00.000Z | Resolved | Connectivity Issue | Continues monitoring and reporting. | 3rd floor Heritage tower | 201471988 | INC_26_020126 | Their CMS went off and it was not able to communicate with the TMC on central (172.16.30.6). | 2026-02-09T07:10:00.000Z | Internal | Mobile Money / Vasgate
Issue was escalated to the NIB team ¦¦Issue was resolved by the NIB team | NIB | System Downtime | 2026-02-08T02:00:00.000Z | NIB server was not accessible resulting in transactions not coming in. | Eric Fillipe Arthur | 355 | 2026-02-08T07:55:00.000Z | Resolved | Connectivity Issue | Continues monitoring and seeking rapid updates until issue is resolved. | 3rd floor Heritage tower | 201471988 | INC_26_020125 | NIB server was not accessible resulting in transactions not coming in. | 2026-02-08T02:00:00.000Z | External | Mobile Money / Vasgate
An Email was sent to clients regarding the maintenance | All | System Downtime | 2026-02-08T01:00:00.000Z | All services were down because of the maintenance by the network team | Maxwell Eshun | 120 | 2026-02-08T03:00:00.000Z | Resolved | System Maintenance | Continuous monitoring and asking for updates till issue is resolved | 3rd floor Heritage tower | 533866740 | INC_26_020124 | Network team had maintenance to perform causing all transactions to fail | 2026-02-08T01:00:00.000Z | Internal | All Systems
Issue was esclated to the Bestpoint team¦¦Issue was resolved at their end | Bestpoint | System Downtime | 2026-02-05T11:18:00.000Z | Transactions were failing because we could not connect to their host | Harry Opata | 124 | 2026-02-05T13:17:00.000Z | Resolved | Connectivity Issue | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_020123 | We could not connect to their host. | 2026-02-05T11:13:00.000Z | External | All transaction.
We communicated with NIB via WhatsApp | NIB | System Downtime | 2026-02-04T11:30:00.000Z | A limit was made on the NIB mobile transactions which was causing transactions to fail | Fredrick Hanson | 183 | 2026-02-04T14:33:00.000Z | Resolved | Connectivity Issue | Continuously verify service availability and coordinate with all relevant personnel to support the investigation and resolution of the issue. | 3rd floor Heritage tower | 552150123 | INC_26_020122 | Limit made on the NIB mobile transaction | 2026-02-04T11:30:00.000Z | Internal | NIB mobile App transactions
Issue was escalated tO technical operations team¦¦Issue was resolved by the same team | Atwima | System Downtime | 2026-02-02T23:16:00.000Z | We lost connectivity to their service due to binding issues | Maxwell Eshun | 778 | 2026-02-03T12:14:00.000Z | Resolved | Connectivity Issue | Continuous monitoring and asking for update till issue is resolved | 3rd floor Heritage tower | 533866740 | INC_26_020121 | Binding issue | 2026-02-02T23:16:00.000Z | Internal | Mobile Money and Vasgate
Transactions were switched to OVA and finance was informed | Abii National¦¦Bestpoint¦¦BOA¦¦NIB¦¦PBL¦¦SISL¦¦VisionFund¦¦Atwima | System Downtime | 2026-02-03T13:20:00.000Z | GHIPSS was down causing transactions to fail, so we switched to OVA for transactions to start processing fine | Fredrick Hanson | 155 | 2026-02-02T21:15:00.000Z | Resolved | System Maintenance | There must be a continuous monitoring and asking of update from their team on the issue. | 3rd floor Heritage tower | 552150123 | INC_26_020120 | GHIPSS was down causing transactions to fail | 2026-02-02T18:40:00.000Z | External | All transactions passing GHIPSS
The issue was escalated to Comsis | All | System Downtime | 2026-01-31T12:00:00.000Z | We couldn't connect to our ISP | Mary Asante | 120 | 2026-01-31T14:00:00.000Z | Resolved | Connectivity Issue | We should monitor closely to detect such issues on time | 3rd floor Heritage tower | 534488985 | INC_26_010118 | Internet issue | 2026-01-31T12:00:00.000Z | External | All transactions
The issue was resolved by our technical team | Atwima | System Downtime | 2026-01-31T18:00:00.000Z | Transactions were throwing 96 | Harry Opata | 900 | 2026-01-31T19:00:00.000Z | Resolved | Connectivity Issue | We should monitor closely to detect such issues on time | 3rd floor Heritage tower | 256591308 | INC_26_020119 | Binding | 2026-01-31T04:00:00.000Z | Internal | Credit and Top up transactions
The Issue was escalated to the ABII team via whatsapp.¦¦The issue was resolved at their end | Abii National | System Downtime | 2026-01-26T04:00:00.000Z | All Transactions were failing because we could not connect to their host. | Harry Opata | 60 | 2026-01-27T05:00:00.000Z | Resolved | Connectivity Issue | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_010115 | We could not connect to their Host | 2026-01-27T04:00:00.000Z | External | All Transactions
Cloudflare Routing / Security Rules were updated to explicitly allow Multichoice IP addresses.¦¦The rule change was applied successfully.¦¦Issue was escalated to the Multichoice team | Multi Choice | System Downtime | 2026-01-26T14:58:00.000Z | It was observed that transactions from Multichoice were no longer being received, while transactions from other merchants continued to process successfully through the same endpoint. This indicated that the issue was merchant-specific rather than a platform-wide outage. | Mary Asante | 2701 | 2026-01-28T11:57:00.000Z | Resolved | Connectivity Issue | We should monitor continuously to detect such issues on time | 3rd floor Heritage tower | 534488985 | INC_26_010117 | Cloudflare security rules automatically blocked Multichoice IP addresses, preventing their requests from reaching the proxy server. As a result, Cloudflare returned HTTP 403 responses to Multichoice, causing transaction failures. | 2026-01-26T14:56:00.000Z | External | All Multichoice transactions
The Issue was escalated to the MTN team.¦¦The issue was resolved by the MTN team | MTN | System Downtime | 2026-01-25T18:50:00.000Z | There were delays on debit transactions. | Harry Opata | 383 | 2026-01-26T00:00:00.000Z | Resolved | Others | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_010116 | There were delays on debit transactions. | 2026-01-25T17:37:00.000Z | External | DEBIT TANSACTIONS
A mail was sent to various clients¦¦All clients were informed via whatsApp as well | MTN | System Downtime | 2026-01-24T19:43:00.000Z | MTN Mobile money transactions were failing intermitently | Fredrick Hanson | 348 | 2026-01-25T01:31:00.000Z | Resolved | Connectivity Issue | There must be a continuous monitoring and asking of update from their team on the issue. | 3rd floor Heritage tower | 552150123 | INC_26_010114 | MTN were experiencing technical issues from their end causing MoMo transactions to fail intermitently | 2026-01-24T19:43:00.000Z | External | MTN Mobile money transactions
We contacted the NIB team via WhatsApp¦¦We contacted the NIB Tech team via mail | NIB | System Downtime | 2026-01-23T11:50:00.000Z | Credit transactions were failing intermittently | Fredrick Hanson | 355 | 2026-01-23T17:45:00.000Z | Resolved | Connectivity Issue | There must be a continuous monitoring and asking of update from their team on the issue. | 3rd floor Heritage tower | 552150123 | INC_26_010113 | We could not connect to their host. | 2026-01-23T11:50:00.000Z | External | All Credit transactions (NIB)
Issue was escalated to the DEVOPS team ¦¦DEVOPS team resolved the issue | SISL¦¦PBL | System Downtime | 2026-01-22T13:39:00.000Z | Their USSD went down | Maxwell Eshun | 15 | 2026-01-22T13:54:00.000Z | Resolved | Service / Application not responding | Continuous monitoring and asking for updates till issue is resolved | 3rd floor Heritage tower | 533866740 | INC_26_010112 | The USSD service went down | 2026-01-22T13:39:00.000Z | Internal | Mobile Money
Issue was ecalated to NIB team via Whatsapp and Mail¦¦NIB team restored conncetion from their end | NIB | System Downtime | 2026-01-20T21:00:00.000Z | Transactions were failing because we could not connect to their host | Maxwell Eshun | 145 | 2026-01-20T23:25:00.000Z | Resolved | Connectivity Issue | Continuous monitoring and asking for updates till issue is resolved | 3rd floor Heritage tower | 533866740 | INC_26_010111 | Their host went down | 2026-01-20T21:00:00.000Z | External | Mobile Money and Vasgate
A mail was sent to all client ¦¦The issue was resolved by Team Mtn | MTN | System Downtime | 2026-01-19T11:00:00.000Z | MTN Planned Maintenance | Harry Opata | 1080 | 2026-01-20T05:00:00.000Z | Resolved | System Maintenance | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_010108 | Planned Maintenance | 2026-01-19T11:00:00.000Z | External | All Transactions
We escalated the issue to the PBL team¦¦We blocked all their USSD services | PBL | System Downtime | 2026-01-19T09:00:00.000Z | PBL had a middleware API downtime | Mary Asante | 1200 | 2026-01-20T05:00:00.000Z | Resolved | Connectivity Issue | We should monitor transactions closely to detect such issues on time | 3rd floor Heritage tower | 534488985 | INC_26_010109 | API downtime | 2026-01-19T09:00:00.000Z | External | All PBL transactions
A fix was deployed to both fundgate application | Telecel | System Downtime | 2026-01-18T09:40:00.000Z | All telecel debit on fundgate where failing due to wrong reference being sent to telco. We noticed that "#0000" was appended to all the references being sent to the telco causing failures. | Mary Asante | 2903 | 2026-01-20T10:00:00.000Z | Resolved | Others | We should monitor closely to detect such issues on time | 3rd floor Heritage tower | 534488985 | INC_26_010110 | Still under investigation | 2026-01-18T09:37:00.000Z | Internal | All Telecel debit transactions
The Issue was escalated to the ABII team.¦¦The issue was resolved at their end | Abii National | System Downtime | 2026-01-17T05:32:00.000Z | Transactions were failing because we could not connect to their host | Harry Opata | 70 | 2026-01-17T06:42:00.000Z | Resolved | Connectivity Issue | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_010107 | We could not connect to their host | 2026-01-17T05:32:00.000Z | External | All Transactions
Mails were sent to client ¦¦Issue was resolved by etz team | All | System Downtime | 2026-01-17T00:00:00.000Z | Transactions were not coming because the was a planned maintenance | Harry Opata | 120 | 2026-01-17T02:00:00.000Z | Resolved | System Maintenance | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_010106 | Planned maintenance | 2026-01-17T00:00:00.000Z | Internal | All transactions
A mail was sent to all clients ¦¦All Clients were informed on various pages | All | System Downtime | 2026-01-13T01:28:00.000Z | We were not receiving transaction request and traffick as at 12:45 am, Fundgate could not connect, AWS my sql could not connect, Vasgate could not connect, Virtual bank could not connect. | Fredrick Hanson | 176 | 2026-01-13T03:40:00.000Z | Resolved | Connectivity Issue | Always monitor all services and reach out to the appropraite teams involved | 3rd floor Heritage tower | 552150123 | INC_26_010105 | We were not receiving traffic as we could not connect to fundgate, AWS mysql, VASgate and Virtual Bank | 2026-01-13T00:44:00.000Z | Internal | All clients and Fundgate clients
The Issue was escalated to the ABII team.¦¦The issue was resolved by the ABII team. | Abii National | System Downtime | 2026-01-10T18:26:00.000Z | Transactions were failing because we could not connect to their host. | Harry Opata | 39 | 2026-01-10T19:05:00.000Z | Resolved | Connectivity Issue | There must be a continuous monitoring and asking of update from their team on the issue | 3rd floor Heritage tower | 256591308 | INC_26_010103 | we could not connect to their host. | 2026-01-10T18:26:00.000Z | External | All transactions
Issue was escalated to NIB team¦¦NIB team restored connection from their end | NIB | System Downtime | 2026-01-07T01:32:00.000Z | We could not connect to their host | Maxwell Eshun | 347 | 2026-01-07T07:19:00.000Z | Resolved | Connectivity Issue | Continuous monitoring and asking for update till issue has been resolved | 3rd floor Heritage tower | 533866740 | INC_26_010102 | We were unable to connect to their host causing their transactions to fail | 2026-01-07T01:32:00.000Z | External | Mobile money and Vasgate